## README
BitMach Master Model ¦ v3 detailed EPC, vendor finance and debt structure
This version adds engineer-friendly electrical CAPEX detail, vendor-style miner finance, EPC tranches, external funding and an amortization tab.
What this workbook does | Builds a formula-driven model for (i) the first 12 months of Phase 1 cash flow and burn, and (ii) a simplified 10-year site / solar / compute ramp to 2GW.
Updated / new tabs | Purpose
CAPEX_Electrical_Detail | Exact Hamar T2603-24 electrical quote packages, scope quantities, adders for unpriced items, and normalization into fixed/site + variable/MW electrical CAPEX.
12M_Miner_Vendor | M7DS hardware basis with supplier-style payment mechanics: deposit, vendor-financed balance, monthly principal and interest schedule.
12M_EPC_Tranches | Gross monthly electrical EPC basis and assumed EPC payment tranches / retention finance.
12M_Funding | Equity and senior debt draw schedule sized to monthly funding need, net of arrangement fees.
Debt_Amortization | Indicative 60-month senior debt schedule with interest capitalized during grace and amortization thereafter.
12M_Capex / 12M_Cashflow | Now reference the detailed sheets rather than generic hard-coded timing heuristics for the main hardware / EPC cash spend.

## Control
Control Centre ¦ Edit blue cells only
Core assumptions, logistics, staffing and optional revenue controls.
Driver | Unit | Base Case | Notes
FX (ZAR/USD) | ZAR/USD | 17 | April 2026 investor materials use R17.00/USD for Phase 1 capital framing.
Opening cash | ZAR'000 | 0 | Leave at 0 to see pure burn before financing.
BTC price start | USD/BTC | 75000 | Conservative editable placeholder.
BTC annual growth | % | 0.1 | Editable market assumption.
Network hash start | TH/s | 900000000 | Editable network assumption.
Network hash annual growth | % | 0.15 | Editable market assumption.
Block subsidy | BTC/block | 3.125 | Protocol input.
Fee factor on subsidy | % | 0.1 | Protocol / pool-fee uplift assumption.
Blocks per day | blocks/day | 144 | Protocol input.
Tax rate | % | 0.27 | Placeholder corporate tax rate.
Uptime | % | 0.95 | Operational uptime.
General annual inflation | % | 0.05 | 10Y model escalation.
Salary annual inflation | % | 0.05 | 10Y model escalation.
Grid tariff annual inflation | % | 0.05 | 10Y model escalation.
Phase 1 total gross MW | MW | 20 | Proof phase size.
Grootvlei target MW | MW | 15 | Latest deck uses 15MW Grootvlei + 5MW AMSA for Phase 1.
AMSA target MW | MW | 5 | Latest deck uses 15MW Grootvlei + 5MW AMSA for Phase 1.
Grootvlei hours/day | hours/day | 18 | Conservative proof-phase operating window.
AMSA Eskom hours/day | hours/day | 10 | Solar blend requested in chat.
AMSA solar hours/day | hours/day | 9 | Solar blend requested in chat.
AMSA solar MW year 1 | MW | 10 | Editable management placeholder from chat.
Grootvlei grid tariff | R/kWh | 1 | Year 1 tariff band in materials is R0.80-R1.20/kWh.
AMSA Eskom tariff | R/kWh | 0.9 | Assumes somewhat better blended Eskom leg.
Solar capex | ZAR'000/MW | 7000 | User guidance in chat: ~R7m/MW.
Solar O&M | % p.a. | 0.02 | Solar O&M as % of capex.
Solar COD month | month# | 5 | AMSA solar available during ramp-up.
Miner hashrate | TH/miner | 700 | Top end of working M7DS range; editable.
Miner efficiency | J/T | 12.5 | Management instruction: use M7DS at 12.5J/T.
Miner power | W/miner |  | Formula = hashrate × J/T.
Miner price | USD/miner | 5915 | From latest uploaded workbook; editable.
Aux load | % | 0.05 | Cooling / container auxiliaries.
Miner slots per XS2400 | miners/container | 240 | HeatCore XS2400 working basis.
Hydro container cost | USD/container | 350000 | Hydro container placeholder; replace with quote.
Container gross MW | MW/container |  | Formula from miner power, slot count and aux load.
Miner maintenance | ZAR/miner/year | 2000 | Recurring maintenance per miner.
Electrical/BOS capex | ZAR'000/MW |  | All-in electrical EPC per MW from detailed Hamar quote basis incl adders. Summary use only; monthly/annual sheets now use fixed/site + variable/MW.
Ocean freight | USD/container | 8000 | Editable logistics placeholder.
Port/clearing | ZAR'000/container | 150 | Editable logistics placeholder.
Inland trucking | ZAR'000/container | 120 | Editable logistics placeholder.
Crane/rigging | ZAR'000/container | 100 | Editable logistics placeholder.
Cargo insurance | % | 0.01 | Editable cargo insurance assumption.
Import duty | % | 0.05 | Editable customs placeholder.
Initial spare parts | % | 0.02 | Initial spares as % of hardware capex.
Tools & equipment initial | ZAR'000/site | 750 | Tools, meters, accessories and small equipment.
Office setup / deposits | ZAR'000 | 600 | Corporate office setup / deposits.
Software / SCADA setup | ZAR'000 | 1500 | Initial systems setup.
Legal setup total | ZAR'000 | 1200 | Initial legal documentation.
Staff hardware setup | ZAR'000/FTE | 35 | Laptop / phone / PPE / provisioning.
Fixed corporate FTE | FTE | 6 | Corporate team for first year.
Corporate salary | ZAR'000/FTE/yr | 1000 | Average fully loaded corporate CTC.
Site management FTE/site | FTE/site | 2 | Manager + supervisor per active site.
Site management salary | ZAR'000/FTE/yr | 700 | Average fully loaded site management CTC.
Technicians FTE/MW | FTE/MW | 0.35 | Hydro site technician intensity.
Technician salary | ZAR'000/FTE/yr | 350 | Average fully loaded technician CTC.
Electricians FTE/MW | FTE/MW | 0.08 | Electricians per MW.
Electrician salary | ZAR'000/FTE/yr | 450 | Average fully loaded electrician CTC.
Benefits load | % | 0.2 | Benefits and payroll load.
Travel & accommodation | % | 0.06 | Recurring travel / claims as % of payroll.
Site mobilization travel | ZAR'000/site start | 250 | One-off commissioning / mobilization travel.
SaaS per FTE / month | ZAR'000/FTE/mo | 3.5 | Email, PM, collaboration and security tools.
Site software / monitoring | ZAR'000/site/mo | 40 | SCADA, monitoring and connectivity support.
Legal retainer | ZAR'000/mo | 75 | Ongoing legal support.
Office rent | ZAR'000/mo | 90 | Head office rent.
File storage / cloud | ZAR'000/mo | 25 | Recurring storage and cloud.
Tools / consumables recurring | ZAR'000/MW/mo | 8 | Filters, consumables, small parts.
Security & operating insurance | ZAR'000/site/mo | 120 | Ongoing security and operating insurance.
Other utilities / water | ZAR'000/MW/mo | 20 | Water treatment and misc utilities.
DR in base case? | 0/1 | 0 | Conservative base case default is off.
DR start month | month# | 7 | Optionality start month.
DR price | R/kWh | 0.25 | Conservative DR price placeholder.
DR equivalent hours/day | hours/day | 1.5 | Equivalent paid availability hours.
DR paid utilisation | % | 0.5 | Share of availability window actually paid.
Hyperscaler in base case? | 0/1 | 0 | Conservative base case default is off.
Hyperscaler start month | month# | 13 | After first 12 months by default.
Hyperscaler MW sold | MW | 2 | Pilot tenant power sold.
Hyperscaler hours/day | hours/day | 16 | Conservative pilot tenant run profile.
Hyperscaler sale price | USD/MWh | 130 | Placeholder pilot tariff.
Annual AI/Hyperscaler include? | 0/1 | 0 | 10Y base case default is off.
Annual AI/Hyperscaler start year | year | 2027 | Can switch on from year 2 onward.
Annual AI/Hyperscaler MW share | % | 0.1 | Share of platform MW converted to tenants.
Annual AI/Hyperscaler price | USD/MWh | 130 | Annual AI/HPC price placeholder.
Annual DR include? | 0/1 | 0 | 10Y base case default is off.
Annual DR price | R/kWh | 0.25 | Annual DR price placeholder.
Annual DR equivalent hours/day | hours/day | 1.5 | Annual DR hours placeholder.
Detailed EPC & financing assumptions
Electrical site-fixed share | % of all-in 20MW electrical EPC | 0.25 | Use to split the Hamar 20MW quote into fixed/site cost and variable/MW cost.
Harmonic mitigation allowance | % of quoted electrical EPC | 0.05 | Quote explicitly excludes harmonic mitigation pending Stage 3 spectra; editable allowance.
Lighting / small power allowance | % of quoted electrical EPC | 0.01 | Quote shows lighting blank; editable allowance.
Instrumentation / SCADA allowance | % of quoted electrical EPC | 0.01 | Quote shows instrumentation blank; editable allowance.
Earthing / lightning allowance | % of quoted electrical EPC | 0.02 | Concept basis requires earthing / lightning and wet/high-humidity suitability.
Civil / drainage / fencing allowance | % of quoted electrical EPC | 0.03 | Brownfield enabling works not fully priced in the electrical quote.
Brownfield site similarity factor | x | 1 | 1.00 = use Grootvlei basis as-is for comparable sites; adjust for easier / harder sites.
Miner order lead time | months | 2 | Deposit paid ahead of commissioning.
Miner deposit | % of gross miner order | 0.6 | From attached supplier contract mechanics.
Miner vendor-financed balance | % of gross miner order | 0.4 | From attached supplier contract mechanics.
Miner vendor finance tenor | months | 6 | From attached supplier contract mechanics.
Miner vendor finance interest | % p.a. | 0.06 | Simple annual rate in attached supplier contract.
EPC order lead time | months | 2 | Assumed time from engineering release to energisation for payment staging.
EPC deposit | % of gross EPC package | 0.15 | Assumed notice-to-proceed / mobilization deposit.
EPC procurement/progress payment | % of gross EPC package | 0.35 | Assumed procurement and early progress payment one month before energisation.
EPC installation payment | % of gross EPC package | 0.3 | Assumed payable on site installation / completion of major works.
EPC commissioning / hand-over payment | % of gross EPC package | 0.1 | Assumed payable the month after energisation / hand-over.
EPC vendor-financed retention | % of gross EPC package | 0.1 | Assumed retained / financed amount amortized after commissioning.
EPC vendor finance tenor | months | 12 | Editable placeholder assumption.
EPC vendor finance interest | % p.a. | 0.12 | Editable placeholder assumption.
Equity share of external funding | % | 0.35 | Used in monthly sources-and-uses schedule.
Senior debt share of external funding | % | 0.65 | Used in monthly sources-and-uses schedule.
Senior debt interest rate | % p.a. | 0.13 | Indicative project debt placeholder.
Senior debt tenor | months | 60 | Indicative project debt term.
Senior debt grace period | months | 12 | Interest capitalizes during grace in the amortization tab by default.
Senior debt arrangement fee | % of gross draw | 0.01 | Charged on each debt draw in the funding schedule.
Minimum cash buffer | ZAR'000 | 0 | Keep at 0 to show pure funding need; raise if financiers want a liquidity buffer.
Container order lead time | months | 2 | Container deposit / progress / final cash timing.
Container deposit | % of gross container order | 0.2 | Editable cash timing assumption.
Container progress payment | % of gross container order | 0.3 | Editable cash timing assumption.
Container final payment | % of gross container order | 0.5 | Editable cash timing assumption.
Note on C4: April 2026 investor materials use R17.00/USD for Phase 1 capital framing.
Note on C5: Leave at 0 to see pure burn before financing.
Note on C6: Conservative editable placeholder.
Note on C7: Editable market assumption.
Note on C8: Editable network assumption.
Note on C9: Editable market assumption.
Note on C10: Protocol input.
Note on C11: Protocol / pool-fee uplift assumption.
Note on C12: Protocol input.
Note on C13: Placeholder corporate tax rate.
Note on C14: Operational uptime.
Note on C15: 10Y model escalation.
Note on C16: 10Y model escalation.
Note on C17: 10Y model escalation.
Note on C18: Proof phase size.
Note on C19: Source: Bitmach_Investor_Pres_12_April_2026_Final.pdf p28 shows 15MW Grootvlei + 5MW AMSA for Phase 1.
Note on C20: Source: Bitmach_Investor_Pres_12_April_2026_Final.pdf p28 shows 15MW Grootvlei + 5MW AMSA for Phase 1.
Note on C21: Source context: 09 Feb 2026 Grootvlei Concept Design uses ~19 hours/day normal operation; 31 Mar 2026 Nedbank memo says 18 hours/day is more conservative than 20 hours/day.
Note on C22: Solar blend requested in chat.
Note on C23: Solar blend requested in chat.
Note on C24: Editable management placeholder from chat.
Note on C25: Year-1 Grootvlei grid tariff assumption. Based on the Nedbank memo recommendation to use conservative proof-phase tariffs of roughly R0.80/kWh off-peak and R1.20/kWh day/peak, and the April 2026 investor presentation Year 1 tariff band of R0.80-R1.20/kWh. Source files: Bitmach_Nedbank Business Model and Project monitoring (2).docx; Bitmach_Investor_Pres_12_April_2026_Final.pdf.
Note on C26: Year-1 AMSA grid tariff assumption. Based on the Nedbank memo recommendation to distinguish AMSA economics from Grootvlei, with AMSA benefiting from better blended power economics over time. Source file: Bitmach_Nedbank Business Model and Project monitoring (2).docx.
Note on C27: User guidance in chat: ~R7m/MW.
Note on C28: Solar O&M as % of capex.
Note on C29: Editable miner efficiency input set per user instruction to 12.5 J/T for the model. Working M7DS technical context pack shows a 13.5 J/T +/-5% reference range; this cell is intentionally editable for scenario work. Source file: Grootvlei_20MW_Context_and_Design_Basis.docx plus user instruction in chat.
Note on C30: Editable M7DS hashrate assumption. Working context pack shows WhatsMiner M7DS at 638-702 TH/s. This model uses 700 TH/s as the initial scenario anchor and leaves it user-editable. Source file: Grootvlei_20MW_Context_and_Design_Basis.docx.
Note on C31: Management instruction in chat: use WHATSMINER M7DS - 12.5J/T.
Note on C33: ASIC unit price carried forward as a scenario input from the latest working business-plan workbook and left editable. Update once final OEM quotation is locked.
Note on C34: Cooling / container auxiliaries.
Note on C35: HeatCore XS2400 working basis.
Note on C36: Hydro container price is a working placeholder assumption requiring final EPC/OEM confirmation. The current pack provides container technical bases but not a locked commercial quote.
Note on C38: Recurring maintenance per miner.
Note on C39: Source context: T2603-24 Cost Estimate shows ~R90.6m pilot EPC electrical scope order-of-magnitude.
Note on C40: Editable logistics placeholder.
Note on C41: Editable logistics placeholder.
Note on C42: Editable logistics placeholder.
Note on C43: Editable logistics placeholder.
Note on C44: Editable cargo insurance assumption.
Note on C45: Editable customs placeholder.
Note on C46: Initial spares as % of hardware capex.
Note on C47: Tools, meters, accessories and small equipment.
Note on C48: Corporate office setup / deposits.
Note on C49: Initial systems setup.
Note on C50: Initial legal documentation.
Note on C51: Laptop / phone / PPE / provisioning.
Note on C52: Corporate team for first year.
Note on C53: Average fully loaded corporate CTC.
Note on C54: Manager + supervisor per active site.
Note on C55: Average fully loaded site management CTC.
Note on C56: Hydro site technician intensity.
Note on C57: Average fully loaded technician CTC.
Note on C58: Electricians per MW.
Note on C59: Average fully loaded electrician CTC.
Note on C60: Benefits and payroll load.
Note on C61: Recurring travel / claims as % of payroll.
Note on C62: One-off commissioning / mobilization travel.
Note on C63: Email, PM, collaboration and security tools.
Note on C64: SCADA, monitoring and connectivity support.
Note on C65: Ongoing legal support.
Note on C66: Head office rent.
Note on C67: Recurring storage and cloud.
Note on C68: Filters, consumables, small parts.
Note on C69: Ongoing security and operating insurance.
Note on C70: Water treatment and misc utilities.
Note on C71: 31 Mar 2026 Nedbank memo recommends that demand response remain structured upside / optionality rather than day-one debt support.
Note on C72: Optionality start month.
Note on C73: Demand-response revenue is modeled as optional upside, not base debt support, consistent with the Nedbank memo and investor materials. Source files: Bitmach_Nedbank Business Model and Project monitoring (2).docx; Investment Summary_12_April_2026.pdf.
Note on C74: Equivalent paid availability hours.
Note on C75: Share of availability window actually paid.
Note on C76: 12 Apr 2026 Investment Summary and investor deck position AI/HPC / hyperscaler revenue as a later-layer revenue stream, not required for day-one base economics.
Note on C77: After first 12 months by default.
Note on C78: Pilot tenant power sold.
Note on C79: Conservative pilot tenant run profile.
Note on C80: Placeholder pilot tariff.
Note on C81: Hyperscaler / AI revenue is modeled as off by default in year 1, because current BitMach materials position AI/HPC as a later layer (year 2-3 / Phase 2-3 onward). Source files: Investment Summary_12_April_2026.pdf; Bitmach_Investor_Pres_12_April_2026_Final.pdf.
Note on C82: Can switch on from year 2 onward.
Note on C83: Share of platform MW converted to tenants.
Note on C84: Annual AI/HPC price placeholder.
Note on C85: 10Y base case default is off.
Note on C86: Annual DR price placeholder.
Note on C87: Annual DR hours placeholder.
Note on C88: Phase 1 site split aligned to the latest April 2026 investor presentation: 15MW Grootvlei + 5MW AMSA Vanderbijlpark. Source file: Bitmach_Investor_Pres_12_April_2026_Final.pdf.

## CAPEX_Electrical_Detail
Detailed Electrical CAPEX Basis ¦ Grootvlei Phase 1
Exact Hamar T2603-24 electrical EPC quote packages are used as the cost basis; unpriced items are layered in as explicit editable adders.
Package | Unit | 20MW basis (ZAR'000) | Source / notes
Preliminary & general costs | ZAR'000 | 7142.5 | Exact Hamar summary sheet value.
Engineering & design - engineering | ZAR'000 | 1449.2 | Exact Hamar summary sheet value.
Engineering & design - drafting / DO | ZAR'000 | 358.4 | Exact Hamar summary sheet value.
Main equipment package | ZAR'000 | 49215.6998 | Package includes essential board substation, 100kVA board, control room, RMUs, mini-subs, 100kVA transformer and busduct.
Racking & accessories | ZAR'000 | 204.2202 | Exact Hamar BOQ subtotal.
Cabling | ZAR'000 | 28884.2594 | Exact Hamar BOQ subtotal.
Cable terminations | ZAR'000 | 873.429 | Exact Hamar BOQ subtotal.
Contingency | ZAR'000 | 2500 | Exact Hamar summary sheet value.
Quoted electrical EPC subtotal |  |  | Exact costed packages from the 25 March 2026 Hamar quotation.
Unpriced / under-specified adders
Harmonic mitigation allowance | ZAR'000 |  | Concept comments say harmonic mitigation is required but not allowed for in the preliminary offer.
Lighting / small power allowance | ZAR'000 |  | Lighting line in quote is blank; editable allowance.
Instrumentation / SCADA allowance | ZAR'000 |  | Instrumentation line in quote is blank; editable allowance.
Earthing / lightning allowance | ZAR'000 |  | Concept basis requires earthing / lightning and wet/high-humidity suitability.
Civil / drainage / fencing allowance | ZAR'000 |  | Brownfield electrical quote does not fully price all enabling works.
Adders subtotal |  |  | All editable adders above.
Brownfield similarity factor | x |  | 1.00 = use Grootvlei basis; adjust if another site is easier or harder.
All-in electrical EPC ¦ 20MW | ZAR'000 |  | Exact quote subtotal plus adders, multiplied by the site similarity factor.
Fixed/site cost | ZAR'000/site |  | Editable fixed/site share assumption applied to the all-in 20MW electrical EPC basis.
Variable electrical EPC | ZAR'000/MW |  | Variable portion used to scale incremental MW.
All-in electrical EPC | ZAR'000/MW |  | For reference only.
Quoted scope composition / quantities
Item | Qty | Unit | Notes
3m containerised substation for essential board | 1 | ea | Main equipment package
3m substation switchgear (100kVA board with feeders) | 1 | ea | Main equipment package
6m containerised control room | 1 | ea | Main equipment package
Schneider RMU | 3 | ea | Main equipment package
2MVA mini sub | 20 | ea | Main equipment package
100kVA transformer | 1 | ea | Main equipment package
Busducting from transformer to container (20m) | 12 | ea | Main equipment package
3c x 35mm² 6.6/11kV XLPE cable | 150 | m | Cabling subtotal
1c x 150mm² 6.6/11kV XLPE cable | 2100 | m | Cabling subtotal
1c x 500mm² 6.6/11kV XLPE cable | 9000 | m | Cabling subtotal
1c x 70mm² G/Y insulated earth | 11250 | m | Cabling subtotal
3c x 35mm² 6.6/11kV XLPE cable joint | 2 | joint | Cable termination subtotal
1c x 150mm² 6.6/11kV XLPE cable joint | 72 | joint | Cable termination subtotal
1c x 500mm² 6.6/11kV XLPE cable joint | 18 | joint | Cable termination subtotal
Scope boundary note |  |  | Hamar email thread states the EPC scope includes all electrical works from the 6.6kV feeders to the 400V connection at the BitMach containers, including the essential section and the DX-issued metering scope.
Design note |  |  | The concept comments note that harmonic mitigation is required but was not allowed for in the preliminary offer pending detailed miner harmonic data.

## 12M_Deployment
12-Month Phase 1 Deployment
Edit only the blue MW schedule rows. Base case: Grootvlei ramps first, AMSA follows, and AMSA solar comes online during the ramp.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Days in month | days | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 31 | 30 | 31
Grootvlei closing MW | MW | 0 | 0 | 5 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
AMSA closing MW | MW | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5
AMSA solar closing MW | MW | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Grootvlei opening MW | MW | 1: 0
AMSA opening MW | MW | 1: 0
AMSA solar opening MW | MW | 1: 0
Grootvlei average MW | MW
AMSA average MW | MW
AMSA average solar MW | MW
Total average MW | MW
Grootvlei new MW | MW
AMSA new MW | MW
AMSA solar new MW | MW
Total new MW | MW
Grootvlei active site | flag
AMSA active site | flag
Total active sites | count
Grootvlei site start | flag
AMSA site start | flag
Total site starts | count
Grootvlei closing containers | containers
AMSA closing containers | containers
Total closing containers | containers
Grootvlei opening containers | containers | 1: 0
AMSA opening containers | containers | 1: 0
Total opening containers | containers
Grootvlei new containers | containers
AMSA new containers | containers
Total new containers | containers
Grootvlei closing site FTE | FTE
AMSA closing site FTE | FTE
Total closing site FTE | FTE
Total closing FTE incl corporate | FTE
Total opening FTE incl corporate | FTE
New FTE onboarded | FTE
Grootvlei average miners | miners
AMSA average miners | miners
Total average miners | miners
Grootvlei effective hashrate | TH/s
AMSA effective hashrate | TH/s
Total effective hashrate | TH/s
Grootvlei Eskom energy | MWh
AMSA total energy | MWh
AMSA solar energy used | MWh
AMSA Eskom energy | MWh
Total energy used | MWh
Total Eskom energy used | MWh
Total solar energy used | MWh
Note on D7: Base case schedule: Grootvlei ramps first to 15MW.
Note on I8: Base case schedule: AMSA begins commissioning once Grootvlei proof is underway.
Note on H9: AMSA solar is an explicit build item so the model can capture solar capex and solar O&M separately.

## 12M_Revenue
12-Month Revenue Build
BTC revenue is base case. Demand response and hyperscaler rows are built, but default to OFF in base case.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
BTC price (USD) | USD/BTC
BTC price (ZAR) | ZAR/BTC
Network hash (TH/s) | TH/s
Network BTC mined | BTC/month
Grootvlei BTC mined | BTC/month
AMSA BTC mined | BTC/month
Total BTC mined | BTC/month
BTC revenue | ZAR'000
Demand response revenue - base case | ZAR'000
Demand response revenue - upside | ZAR'000
Hyperscaler revenue - base case | ZAR'000
Hyperscaler revenue - upside | ZAR'000
Total revenue - base case | ZAR'000
Total revenue - with upside | ZAR'000

## 12M_Opex
12-Month Operating Cost Build
Covers site energy cost, payroll, benefits, travel, software, legal, office, tools, security, insurance and utilities.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Grootvlei electricity cost | ZAR'000
AMSA Eskom electricity cost | ZAR'000
AMSA solar O&M | ZAR'000
Total energy cost | ZAR'000
Corporate payroll | ZAR'000
Site management payroll | ZAR'000
Technician payroll | ZAR'000
Electrician payroll | ZAR'000
Gross payroll | ZAR'000
Benefits | ZAR'000
Salaries & benefits | ZAR'000
Travel / accommodation | ZAR'000
Software / storage / monitoring | ZAR'000
Legal fees | ZAR'000
Office rent | ZAR'000
Tools / consumables recurring | ZAR'000
Security & operating insurance | ZAR'000
Other utilities / water | ZAR'000
Total cash opex | ZAR'000
EBITDA - base case | ZAR'000
EBITDA - with upside | ZAR'000

## 12M_Capex
12-Month Capex & Deployment Spend
This sheet now pulls detailed electrical EPC and miner vendor finance logic from dedicated tabs. Edit a few assumptions in Control and the full cash-timing logic updates.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
New MW commissioned | MW
New containers commissioned | containers
New solar MW | MW
New FTE onboarded | FTE
ASIC hardware capex basis | ZAR'000
Hydro container capex basis | ZAR'000
Electrical EPC basis (fixed/site + variable/MW) | ZAR'000
Solar PV capex basis | ZAR'000
Initial spare parts basis | ZAR'000
Tools/equipment initial basis | ZAR'000
Staff hardware basis | ZAR'000
Freight basis | ZAR'000
Port/clearing basis | ZAR'000
Inland trucking basis | ZAR'000
Crane/rigging basis | ZAR'000
Cargo insurance basis | ZAR'000
Import duty basis | ZAR'000
Office/software/legal setup basis | ZAR'000
ASIC hardware cash spend (deposit + vendor installments) | ZAR'000
Hydro container cash spend (editable staged terms) | ZAR'000
Electrical EPC cash spend (tranches + financed retention) | ZAR'000
Solar PV cash spend | ZAR'000
Initial spare parts cash spend | ZAR'000
Tools/equipment initial cash spend | ZAR'000
Staff hardware cash spend | ZAR'000
Freight cash spend | ZAR'000 | 12: 0
Port/clearing cash spend | ZAR'000 | 12: 0
Inland trucking cash spend | ZAR'000 | 12: 0
Crane/rigging cash spend | ZAR'000
Cargo insurance cash spend | ZAR'000 | 12: 0
Import duty cash spend | ZAR'000 | 12: 0
Office/software/legal setup cash spend | ZAR'000
Total capex cash spend | ZAR'000
Cumulative capex spend | ZAR'000

## 12M_Miner_Vendor
12-Month Miner Commercial Schedule
Uses M7DS technical / price assumptions from the model, and applies supplier-style payment mechanics from the attached contract as a placeholder until a final M7DS-specific term sheet is inserted.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
New MW commissioned | MW
Gross hardware capex basis | ZAR'000
New miners commissioned | miners
Deposit cash due | ZAR'000
Vendor-financed principal originated | ZAR'000
Opening vendor payable | ZAR'000
Scheduled principal | ZAR'000
Scheduled interest | ZAR'000
Total hardware cash payment | ZAR'000
Closing vendor payable | ZAR'000
Principal by origination month
Origin month | Source tranche | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Origin 1
Origin 2
Origin 3
Origin 4
Origin 5
Origin 6
Origin 7
Origin 8
Origin 9
Origin 10
Origin 11
Origin 12
Interest by origination month
Origin month | Source tranche | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Origin 1
Origin 2
Origin 3
Origin 4
Origin 5
Origin 6
Origin 7
Origin 8
Origin 9
Origin 10
Origin 11
Origin 12
Commercial note |  | Month 1: Attached supplier contract mechanics used in the model: 60% deposit, 40% balance over 6 monthly installments, 6% simple annual interest, EXW delivery, and buyer-borne logistics / insurance.
Transparency note |  | Month 1: The attached commercial document itself references M73s hardware, not M7DS. In this model, the financing mechanics are used as the placeholder commercial template, while the selected hardware remains WhatsMiner M7DS per management instruction.

## 12M_EPC_Tranches
12-Month Electrical EPC Tranches
Uses the Hamar 20MW electrical EPC basis and assumed EPC payment mechanics. Scope note: 6.6kV feeders to 400V container connections, including essential section and DX metering scope.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Gross electrical EPC basis | ZAR'000
Deposit cash due | ZAR'000
Procurement / progress payment | ZAR'000
Installation payment | ZAR'000
Commissioning / hand-over payment | ZAR'000
Vendor-financed retention originated | ZAR'000
Opening EPC payable | ZAR'000
Scheduled principal | ZAR'000
Scheduled interest | ZAR'000
Total EPC cash payment | ZAR'000
Closing EPC payable | ZAR'000
Principal by origination month
Origin month | Source tranche | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Origin 1
Origin 2
Origin 3
Origin 4
Origin 5
Origin 6
Origin 7
Origin 8
Origin 9
Origin 10
Origin 11
Origin 12
Interest by origination month
Origin month | Source tranche | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Origin 1
Origin 2
Origin 3
Origin 4
Origin 5
Origin 6
Origin 7
Origin 8
Origin 9
Origin 10
Origin 11
Origin 12
Scope note |  | Month 1: Hamar email thread: the EPC scope includes all electrical works from the 6.6kV feeders to the 400V connection at the BitMach containers, and includes the essential section and DX-issued metering scope.
Engineering note |  | Month 1: Concept comments: harmonic mitigation is required for the non-linear mining load, but was not allowed for in the preliminary offer because detailed harmonic spectra were not yet available.

## 12M_Cashflow
12-Month Cash Flow & Burn
Base case still excludes DR and hyperscaler revenue unless switched on; external funding is now formula-driven via the 12M_Funding sheet.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Revenue - base case | ZAR'000
Revenue - with upside | ZAR'000
Cash opex | ZAR'000
EBITDA - base case | ZAR'000
Capex cash spend | ZAR'000
Unlevered cash flow - base case | ZAR'000
Unlevered cash flow - with upside | ZAR'000
Net external funding input | ZAR'000
Opening cash | ZAR'000
Ending cash | ZAR'000
Cumulative burn before funding | ZAR'000
Peak funding required | ZAR'000
Equity draw | ZAR'000
Senior debt draw | ZAR'000
Phase 1 Year-1 Summary
Total BTC mined | BTC
Total revenue - base | ZAR'000
Total cash opex | ZAR'000
Total capex cash spend | ZAR'000
Year-1 unlevered cash burn | ZAR'000
Peak funding required | ZAR'000
Total external funding | ZAR'000
Total equity drawn | ZAR'000
Total senior debt drawn | ZAR'000
Ending cash in month 12 | ZAR'000
Note on D12: Optional funding line. Add equity or debt draws here if you want to see a funded cash balance.

## 12M_Funding
12-Month External Funding Schedule
This sheet sizes external equity and senior debt draws to the monthly funding need after vendor-style miner and EPC payment structures.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Opening cash before external funding | ZAR'000
Unlevered cash flow before external funding | ZAR'000
Required net external funding | ZAR'000
Equity draw | ZAR'000
Senior debt gross draw | ZAR'000
Debt arrangement fee | ZAR'000
Net external funding input | ZAR'000
Closing cash after external funding | ZAR'000
Cumulative equity drawn | ZAR'000
Cumulative senior debt drawn | ZAR'000

## Debt_Amortization
Senior Debt Amortization Schedule
By default, interest capitalizes during the grace period and is paid in cash only once amortization starts. Adjust tenor, grace and rate in Control.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
|  | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27 | Jan-28 | Feb-28 | Mar-28 | Apr-28 | May-28 | Jun-28 | Jul-28 | Aug-28 | Sep-28 | Oct-28 | Nov-28 | Dec-28 | Jan-29 | Feb-29 | Mar-29 | Apr-29 | May-29 | Jun-29 | Jul-29 | Aug-29 | Sep-29 | Oct-29 | Nov-29 | Dec-29 | Jan-30 | Feb-30 | Mar-30 | Apr-30 | May-30 | Jun-30 | Jul-30 | Aug-30 | Sep-30 | Oct-30 | Nov-30 | Dec-30
Opening debt balance | ZAR'000
New senior debt draw | ZAR'000
Interest accrued | ZAR'000
Scheduled principal | ZAR'000
Debt service cash | ZAR'000
Closing debt balance | ZAR'000
Cumulative draws | ZAR'000
Cumulative interest | ZAR'000

## 10Y_Ramp
10-Year Site & Solar Ramp
Blue rows are the long-dated platform build assumptions. Base case reaches 2GW by 2034/2035.
|  | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
|  | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Grootvlei compute MW | MW | 15 | 40 | 60 | 80 | 100 | 120 | 140 | 160 | 180 | 200
AMSA VB compute MW | MW | 5 | 40 | 120 | 200 | 220 | 230 | 240 | 250 | 250 | 250
AMSA Newcastle compute MW | MW | 0 | 20 | 80 | 150 | 220 | 300 | 360 | 430 | 500 | 500
Saldanha compute MW | MW | 0 | 20 | 80 | 120 | 220 | 300 | 360 | 430 | 500 | 500
Komati compute MW | MW | 0 | 60 | 130 | 150 | 440 | 450 | 500 | 530 | 570 | 550
Total compute MW | MW
AMSA VB solar MW | MW | 10 | 180 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
AMSA Newcastle solar MW | MW | 0 | 0 | 50 | 100 | 150 | 200 | 250 | 250 | 250 | 250
Saldanha solar MW | MW | 0 | 0 | 0 | 50 | 100 | 150 | 200 | 250 | 250 | 250
Komati solar MW | MW | 0 | 0 | 0 | 20 | 40 | 60 | 80 | 100 | 120 | 150
Total solar MW | MW
Note on D7: Annual compute MW ramp is user-editable. Current profile reflects a strategic scaling path to 2,000MW over 10 years, as requested in chat, while staying directionally consistent with BitMach materials describing a 20MW proof-of-concept scaling to 500MW-2GW.

## 10Y_Model
10-Year Platform Model
Simplified annual portfolio model. Phase 1 monthly sheet is the authoritative view for year one; this annual view supports strategic sizing and stress tests.
|  | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
|  | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Total compute MW | MW
Total solar MW | MW
Installed miners | miners
Effective hashrate | TH/s
BTC mined | BTC/yr
BTC revenue | ZAR'000
DR revenue - base case | ZAR'000
AI/Hyperscaler revenue - base case | ZAR'000
Total revenue - base case | ZAR'000
GVL energy cost | ZAR'000
AMSA VB energy cost | ZAR'000
Newcastle energy cost | ZAR'000
Saldanha energy cost | ZAR'000
Komati energy cost | ZAR'000
Solar O&M | ZAR'000
Total energy cost | ZAR'000
Salaries & benefits | ZAR'000
Admin / travel / software / office / legal | ZAR'000
Security / tools / utilities | ZAR'000
Total cash opex | ZAR'000
EBITDA | ZAR'000
New MW | MW
New solar MW | MW
New containers | containers
Miner capex | ZAR'000
Container capex | ZAR'000
Electrical EPC capex (site-fixed + variable/MW) | ZAR'000
Solar capex | ZAR'000
Logistics / duties / spares | ZAR'000
Total capex | ZAR'000
Annual cash flow before financing | ZAR'000

## Checks
Model Checks
Check | Formula / Output | Interpretation | Status
Phase 1 total MW closes at 20 |  | Should equal 20MW
M7DS efficiency input |  | Should equal 12.5 J/T
Base-case DR revenue |  | Should be 0 if DR flag is off
Base-case hyperscaler revenue |  | Should be 0 if hyperscaler flag is off
10Y ramp hits 2GW |  | Should equal 2,000MW
No negative ending cash if funding added |  | Without funding this can be negative; add funding if needed
Phase 1 year-1 BTC mined |  | Informational | INFO
Peak funding required |  | Informational | INFO
Electrical EPC basis date | 25 Mar 2026 | T2603-24 quote date | INFO
Miner vendor finance shares sum to 100% |  | Should equal 1.00
EPC tranche shares sum to 100% |  | Should equal 1.00
External funding shares sum to 100% |  | Should equal 1.00
Funding sheet closes to cashflow |  | Should equal 0
Year-1 ending cash after funding |  | Informational | INFO